## Agile Project Charter
PiRail - AGILE PROJECT CHARTER
Monitoring railroad health using minimal equipment and investment.
PROJECT NAME
PiRail
PROJECT CHAMPION |  | PROJECT SPONSOR | PROJECT MANAGER
|  | John Miner | Craig Smith
STAKEHOLDERS
Jon Miner, Rail Companies
EXPECTED START DATE |  | EXPECTED DATE OF COMPLETION | DATE OF DOCUMENT
2025-09-08 |  | 2026-04-21 | 2025-09-15
PROJECT DETAILS
VISION | Take existing PiRail capabilities and expand upon them, focusing on data management and analysis. Creating capabilities to do real-time data analysis that could automate POIs, Improving data management for user experience and convienience, and setting up a baseline for future video collection and analysis.
SUCCESS METRICS | 1. Inseting modules to look at abnormalities and generate points of interest automatically. The POI then displayed on a map to show a user. Measuring accuracy of the POIs to ensure correctness. 2. Redesigned web server that is simple and easy for users. 3. Research done on video collection and analysis
RISKS | Missing rail defects and causing a train derailment or other accident, or creating false positives that don't need maintenance resulting in mispending money instead of improving rail lines
Roadmap
POC Description |  | Epics
The PiRail 2026 Proof Of Concept should consist of a new map coverage page where Points of Interst are recorded in a segmented map, where sections can be downloaded for offline use. Points of Interest are recorded via the analysis of live sensor data in a new data analysis model. The data can also be viewed via the IMU page which will show a strip chart of the live data and can have it's z-axis, roll, and speed configured |  | Build new map coverage page
Create URC Poster: Outline poster in Sprint 3 Create draft in Sprint 4 Submit Final in Sprint 7
Update IMU page to show strip chart of z-axis, roll and speed
Design data analysis module
Get familiar with project, set up repos, access remote testbed
Investigation
POC Roadmap Image
#VALUE!
Stories
As an inspector, I want to attach photos and notes to each POI I log, so that others can understand the severity and type of issue
As a student, I would like to be able to plot a point of interest on a map so that it can be checked for accuracy/plausibility.
As an inspector, I want offline functionality for logging POIs, so that I can still record issues in areas with no internet connection.
As a student developer, I want to connect the app to a cloud database, so POIs are stored centrally and accessible across devices.
As a supervisor, I want to filter POIs by severity, age, and location, so I can prioritize resource allocation.
As a data analyst, I want to analyze trends in POI data (recurring defect types or risk zones), so we can make preventative improvements.
As a student tester, I want to simulate offline usage and reconnection, so we can confirm that POIs logged without internet are uploaded later.
As an analyst, I would like to be able to format IMU data so that it can be fed to machine learning models.
As a user, I want a real-time IMU strip chart (z‑axis, roll, speed) so I can see the live signal like a seismograph.
As a user, I want abnormal points highlighted on the strip chart, so spikes are obvious.
As an analyst, I would like to visualize a single component of continuous IMU data so that I can look for trends.
As a user, I want thresholds adjustable in real time, so detection remains robust across conditions.
As a user, I want to download OpenStreetMap/OpenRailwayMap tiles for a route before going offline, so maps work in the field.
As a student presenter, I want a first draft of the URC poster with problem, method (IMU + pipeline), and preliminary results, so the team can iterate with the sponsor.
As a railroad inspector I would like to see potential points of interest conveniently
As a student, I would like to be able to test the results generated by the interface.